## Slide 1: MONIMET Actions B7, C2 EU Life12 ENV/FI/000409
Maria Holmberg, Anu Akujärvi, Katri Rankinen, SYKE, Monimet kick-off, 17.9.2013

## Slide 2: Demonstration on ecosystem services and vulnerability
MONIMET Action B7
SYKE, FMI, METLA, UHEL
Tasks
  Ecosystem service provision potential
    Indicators (using results of B1- B6)
      Carbon sequestration
      Nitrogen retention
  Vulnerability assessment
    Climate change scenarios
    Risk for decrease in the provision of ecosystem services

## Slide 3: Demonstration on ecosystem services and vulnerability
MONIMET Action B7
SYKE, FMI, METLA, UHEL
Deliverables
  Ecosystem provision potential and vulnerability to climate change in Climateguide.fi 15.6.2017
Milestones
  Method survey completed 31.3.2014
  Data compilation completed 31.3.2015
  Assessment of ecosystem service provision potential completed 30.11.2015
  Vulnerability assessment completed 30.11.2016

## Slide 4: Demonstration on ecosystem services and vulnerability
MONIMET Action B7
SYKE, FMI, METLA, UHEL
Next tasks
  Method survey
    Ecosystem service indicators
    Valuation of ecosystem services
  Data compilation

## Slide 5: Vulnerability assessment
Climate change indicators
Mass balance models
Carbon sequestration (Biomass model, Yasso07)
Spatially explicit data
Socio-economic data
Land cover
Nitrogen retention (Inca-N, Vemala)
Ecosystem services
Vulnerability assessment
Maps
Statistic
Provision potential
Change in potential
The vulnerability assessment will result in maps and statistics and utilize the climate change
indicators as results of mass balance models, spatially explicit data and methods to assess
ecosystem service provision potential and predicted changes in the potential.

## Slide 6: Monitoring of socio-economic impact
MONIMET Action C2
SYKE, FMI, METLA, UHEL
Aim to assess the awareness of local population
    Role of forests in carbon balance
    Vulnerability of municipalities to climate change
Tasks
  Surveys
    Targeted to local population
      Lepsämänjoki
      Hämeenlinna

## Slide 7: Monitoring of socio-economic impact
MONIMET Action C2
SYKE, FMI, METLA, UHEL
Deliverables
  Contribution to final report 1.9.2017
Milestones
  1st survey on public awareness 31.1.2014
  2nd survey on public awareness 1.6.2017
Next tasks
  1st survey
    Background status in VACCIA
    Contacts to stakeholders